## Sheet1
Change Request Log
Project ID
Project Name
S.No | Change Request Number | Request / Issue / Incident Description | Application Impact | Type | Priority | Rqueset From | Raised by Team | Reported date | Engineer | Planned Effort(hrs) | Actual Effort(hrs) | Effort Variance | In Progress | Target Close Date | Days Open | Actual Date of Closure | Month | Remarks
1 | CRN001 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-22 | Pravin R |  |  |  | Completed | 2026-06-22 | 1 |  | 2026-06 | I have finished my onboarding and studied intermediate Java.
2 | CRN002 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-23 | Pravin R |  |  |  | Completed | 2026-06-23 | 1 |  | 2026-06 | I have studied MYSQL database
3 | CRN003 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-24 | Pravin R | 4 | 2 |  | Completed | 2026-06-24 | 1 | 2026-06-24 | 2026-06 | Java CRUD operations using OOP and Studied Spring boot and MYSQL joins
3 | CRN003 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-24 | Pravin R | 6 | 5 |  | Completed | 2026-06-25 | 2 | 2026-06-25 | 2026-06 | I built complete CRUD operations using React, Node.js and MySQL and Studied Spring boot
5 | CRN005 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-25 | Pravin R | 7 | 7 |  | Completed | 2026-06-26 | 2 | 2026-06-26 | 2026-06 | Delivered an integrated Student Form for secure authentication and data visualization using react, node.js and mysql
6 | CRN006 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-26 | Pravin R | 9 | 13 |  | Completed | 2026-06-29 | 2 | 2026-06-29 | 2026-06 | Delivered integrated Signup, Login, and Student Details pages with database persistence using react, java and mysql
7 | CRN007 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-27 | Pravin R | [7 empty] | 2026-06 | Holiday
8 | CRN008 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-28 | Pravin R | [7 empty] | 2026-06 | Holiday
9 | CRN009 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-29 | Pravin R | 2 | 1 |  | Completed | 2026-06-29 | 1 | 2026-06-29 | 2026-06 | update the edit options in studen form and Studied Spring boot
10 | CRN010 | Org Structure for JAVA |  |  |  |  | IT | 2026-06-30 | Pravin R | 12 | 19 |  | Completed | 2026-07-02 | 3 | 2026-07-02 | 2026-07 | Next update Integrated email-based OTP verification login page in studen form portal
11 | CRN011 | Org Structure for JAVA |  |  |  |  | IT | 2026-07-01 | Pravin R |  |  |  | Completed | 2026-07-02 | 2 | 2026-07-02 | 2026-07 | Error Fixed login by correcting JSON data, missing libraries, and CORS.
12 | CRN012 | Org Structure for JAVA |  |  |  |  | IT | 1900-01-01 | Pravin R |  |  |  | Completed | 2026-07-02 | 1 | 2026-07-02 | 2026-07 | Completed Integrated email-based OTP verification login page in studen form portal
13 | CRN013 | Org Structure for JAVA |  |  |  |  | IT | 2026-07-02 | Pravin R |  |  |  | Progress | 2026-07-03 | 2 | 2026-07-03 | 2026-07 | Update After logging in, users redirect to their student profile page, while new users navigate to the student form page
14 | CRN014 | Org Structure for JAVA |  |  |  |  | IT | 2026-07-03 | Pravin R |  |  |  |  | 2026-07-03 |  | 2026-07-03 | 2026-07
15 | CRN015 | Org Structure for JAVA |  |  |  |  | IT